# Partial Demolition & Rebuild Budget – Museum Project

## Estimated Total Project Cost

Low Range: ~$1.07M
High Range: ~$2.73M

## Purpose

Planning estimate for partial demolition and rebuild of a museum facility.

## Included Phases

1. Pre-Development & Professional Fees
2. Permits & Legal
3. Partial Demolition
4. Site Work & Foundation
5. Structural Build (Shell)
6. Major Systems (MEP)
7. Interior Build-Out
8. Museum-Specific Costs
9. Exterior & Site Improvements
10. Contingency & Soft Costs

## PHASE 1: PRE-DEVELOPMENT & PROFESSIONAL FEES

| Item | Estimated Cost Range |
| --- | --- |
| Feasibility study / site assessment | $5,000 – $15,000 |
| Architectural design (schematic → construction docs) | $25,000 – $75,000 |
| Structural engineer | $8,000 – $20,000 |
| Civil engineer / site plan | $5,000 – $15,000 |
| Historic preservation consultant (if applicable) | $5,000 – $20,000 |
| Survey (boundary + topo) | $3,000 – $7,000 |
| Environmental review (asbestos/lead testing) | $3,000 – $10,000 |
| Phase 1 Subtotal | $54,000 – $162,000 |

## PHASE 2: PERMITS, LEGAL & APPROVALS

| Item | Estimated Cost Range |
| --- | --- |
| Demolition permit | $1,000 – $5,000 |
| Building permits (new construction) | $5,000 – $20,000 |
| Zoning/variance applications (if needed) | $3,000 – $15,000 |
| Legal fees (contracts, land use) | $5,000 – $15,000 |
| Utility disconnect/reconnect fees | $2,000 – $8,000 |
| Phase 2 Subtotal | $16,000 – $63,000 |

## PHASE 3: PARTIAL DEMOLITION

| Item | Estimated Cost Range |
| --- | --- |
| Selective interior demolition | $10,000 – $30,000 |
| Structural separation (protect front half) | $15,000 – $40,000 |
| Full rear-structure demolition | $20,000 – $60,000 |
| Debris hauling & disposal | $8,000 – $25,000 |
| Hazardous material abatement (if found) | $10,000 – $40,000 |
| Temporary shoring & weatherproofing | $5,000 – $15,000 |
| Phase 3 Subtotal | $68,000 – $210,000 |

## PHASE 4: SITE WORK & FOUNDATION (NEW BUILD)

| Item | Estimated Cost Range |
| --- | --- |
| Site clearing & grading | $10,000 – $30,000 |
| Excavation | $15,000 – $40,000 |
| New foundation (slab or crawlspace) | $30,000 – $80,000 |
| Drainage & waterproofing | $10,000 – $25,000 |
| Phase 4 Subtotal | $65,000 – $175,000 |

## PHASE 5: STRUCTURAL BUILD (SHELL)

| Item | Estimated Cost Range |
| --- | --- |
| Framing (wood or light steel) | $60,000 – $150,000 |
| Structural tie-in to existing building | $15,000 – $40,000 |
| Roofing | $25,000 – $60,000 |
| Exterior walls & sheathing | $30,000 – $75,000 |
| Windows & exterior doors | $25,000 – $70,000 |
| Phase 5 Subtotal | $155,000 – $395,000 |

## PHASE 6: MAJOR SYSTEMS (MEP)

| Item | Estimated Cost Range |
| --- | --- |
| Electrical (commercial-grade) | $40,000 – $90,000 |
| Plumbing | $30,000 – $70,000 |
| HVAC (museum-grade climate control) | $50,000 – $120,000 |
| Fire alarm & suppression | $20,000 – $60,000 |
| Data/security systems | $15,000 – $40,000 |
| Phase 6 Subtotal | $155,000 – $380,000 |

## PHASE 7: INTERIOR BUILD-OUT

| Item | Estimated Cost Range |
| --- | --- |
| Insulation & drywall | $30,000 – $70,000 |
| Flooring | $25,000 – $75,000 |
| Ceilings (acoustic/gallery) | $20,000 – $60,000 |
| Interior doors & trim | $15,000 – $40,000 |
| Paint & finishes | $15,000 – $35,000 |
| ADA-compliant restrooms | $25,000 – $60,000 |
| Phase 7 Subtotal | $130,000 – $400,000 |

## PHASE 8: MUSEUM-SPECIFIC COSTS

| Item | Estimated Cost Range |
| --- | --- |
| Exhibit walls & partitions | $20,000 – $75,000 |
| Display cases & mounts | $25,000 – $100,000 |
| Lighting (gallery-grade) | $20,000 – $60,000 |
| Archival storage build-out | $15,000 – $50,000 |
| Wayfinding & signage | $5,000 – $20,000 |
| Phase 8 Subtotal | $85,000 – $305,000 |

## PHASE 9: EXTERIOR & SITE IMPROVEMENTS

| Item | Estimated Cost Range |
| --- | --- |
| Parking/driveways | $20,000 – $60,000 |
| Walkways & ADA ramps | $15,000 – $40,000 |
| Landscaping | $10,000 – $35,000 |
| Exterior lighting | $8,000 – $25,000 |
| Fencing/signage | $5,000 – $20,000 |
| Phase 9 Subtotal | $58,000 – $180,000 |

## PHASE 10: CONTINGENCY & SOFT COSTS

| Item | Estimated Cost Range |
| --- | --- |
| Construction contingency (10–20%) | $120,000 – $350,000 |
| Insurance & bonding | $15,000 – $40,000 |
| Project management | $25,000 – $75,000 |
| Phase 10 Subtotal | $160,000 – $465,000 |

## NEXT STEPS

- Decide target square footage for the new build

- Confirm historic preservation constraints (if any)

- Identify funding strategy (grants, donors, phased build)

- Choose whether to phase construction to reduce upfront cost